## Staffing and Financial Plan
Staffing Plan (Role-Wise Ramp Up) | [7 empty] | P&L and Cashflow Analysis
Role | Monthly Salary (INR) | Q1 (Foundation) | Q2 (Reporting) | Q3 (Payments) | Q4 (Products) | Q5 (Scale) | Q6 (Enterprise) | Financial Metric | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | TOTAL
Project Manager | ₹1,50,000 | 1 | 1 | 1 | 1 | 1 | 1 | Revenue (Sales) | ₹0 | ₹0 | ₹10,00,000 | ₹25,00,000 | ₹50,00,000 | ₹80,00,000 | ₹1,65,00,000
Product Owner | ₹1,50,000 | 1 | 1 | 1 | 1 | 1 | 1
Full Stack Devs | ₹80,000 | 2 | 2 | 2 | 2 | 2 | 2 | Staff Salaries | ₹15.60 L | ₹18.00 L | ₹21.60 L | ₹24.30 L | ₹28.20 L | ₹32.70 L | ₹140.40 L
QA Tester | ₹60,000 | 1 | 1 | 1 | 1 | 1 | 1 | Infra & License | ₹50,000 | ₹50,000 | ₹1,00,000 | ₹1,50,000 | ₹2,50,000 | ₹4,00,000 | ₹10.00 L
UI/UX Designer | ₹80,000 | - | +1 (New) | 1 | 1 | 1 | 1 | Marketing/Ops | ₹50,000 | ₹50,000 | ₹2,00,000 | ₹3,00,000 | ₹5,00,000 | ₹8,00,000 | ₹19.00 L
Sr. Backend Eng. | ₹1,20,000 | - | - | +1 (New) | 1 | 1 | 1 | Total Expenses | ₹16.60 L | ₹19.00 L | ₹24.60 L | ₹28.80 L | ₹35.70 L | ₹44.70 L | ₹169.40 L
Business Analyst | ₹90,000 | - | - | - | +1 (New) | 1 | 1
DevOps Engineer | ₹1,30,000 | - | - | - | - | +1 (New) | 1 | NET PROFIT / LOSS | (₹16.6 L) | (₹19.0 L) | (₹14.6 L) | (₹3.8 L) | ₹14.3 L | ₹35.3 L | (₹4.4 L)
Security Specialist | ₹1,50,000 | - | - | - | - | - | +1 (New) | Cumulative Cashflow | (₹16.6 L) | (₹35.6 L) | (₹50.2 L) | (₹54.0 L) | (₹39.7 L) | (₹4.4 L)
TOTAL HEADCOUNT |  | 5 | 6 | 7 | 8 | 9 | 10
Quarterly Staff Cost |  | ₹15,60,000 | ₹18,00,000 | ₹21,60,000 | ₹24,30,000 | ₹28,20,000 | ₹32,70,000
Key Insights for Investors:
Peak Burn: The project reaches its maximum cash deficit (lowest point in cashflow) in Q4 at -₹54 Lakhs. This is the investment required to survive until profitability.
|  |  |  | Quarter | Staff Cost (Lakhs)
|  |  |  | Q1 | 15.6 |  |  | Break-Even Point: The project turns operationally profitable in Q5 (making ₹14.3L profit that quarter).
|  |  |  | Q2 | 18
|  |  |  | Q3 | 21.6 |  |  | ROI Horizon: By the end of Q6, the cumulative loss is nearly wiped out (only -₹4.4L remaining). The project will be fully net positive by Month 19 (Q7).
|  |  |  | Q4 | 24.3
|  |  |  | Q5 | 28.2 |  |  |  | IMPLIMENTATION ROADMAP
|  |  |  | Q6 | 32.7 |  |  |  | Quarter | Focus Area | Key Objective
[9 empty] | Q1 | Foundation & Security | Migrate from JSON to SQL; implement secure hashed authentication.
[9 empty] | Q2 | Reporting & History | Transaction ledgers, PDF statement generation, and Admin Dashboard.
[9 empty] | Q3 | Digital Payments | Internal fund transfers, beneficiary management, and email notifications.
[9 empty] | Q4 | Financial Products | Loan management module, Fixed Deposits (FD), and interest calculators.
[9 empty] | Q5 | Scale & API | REST API for 3rd party integration, Mobile-responsive UI overhaul.
[9 empty] | Q6 | Enterprise Ready | Multi-branch support, Role-Based Access Control (RBAC), Audit trails.
Product Vision & Mission
Product Vision: To become the most accessible and deployable "Banking-in-a-Box" solution for small cooperative banks, credit societies, and micro-finance institutions, bridging the gap between simple record-keeping and modern digital banking.
Product Mission: To migrate "StreamBank" from a local JSON-based prototype to a secure, cloud-native banking platform that ensures data integrity, regulatory compliance, and seamless customer experience by 2027.

## Story and sprint planning
STORY
S1 (Account Creation): As a new user, I want to create a new account with a unique account number so that I can start managing my finances.
|  |  |  | STORY | VALUE | STORY PTS | PRIORITY | Man hour | SPRINT
| S2 (Data Persistence): As a system admin, I want all user data to be stored locally in a data.json file so that account records are not lost when the app closes. |  |  | S6 (View Details) | 500 | 10 | Low | 100 | 2
|  |  |  | S7 (Update Info) | 500 | 30 | Med |  | 2
| S3 (Authentication): As a user, I want to secure my operations with a PIN so that unauthorized users cannot access my funds. |  |  | S9 (Error Msgs) | 400 | 10 | Med |  | 2
|  |  |  | S2 (Data JSON) | 1200 | 40 | High |  | 2
|  |  |  | S10 (Delete Acct) | 300 | 10 | Low |  | 2
| S4 (Deposit): As a customer, I want to deposit money into my account (up to ₹10,000 per transaction) so that I can increase my balance safely. |  |  | S1 (Create Account) | 1200 | 30 | High | 100 | 1
|  |  |  | S3 (PIN Auth) | 1000 | 20 | High |  | 1
| S5 (Withdrawal): As a customer, I want to withdraw money with an automatic balance check so that I do not overdraw my account. |  |  | S4 (Deposit) | 900 | 20 | High |  | 1
|  |  |  | S5 (Withdraw) | 900 | 20 | High |  | 1
| S6 (View Details): As a user, I want to view my account details (Name, Balance, Email) after entering my PIN so I can track my financial status. |  |  | S8 (Unique IDs) | 700 | 10 | High |  | 1
S7 (Update Profile): As a user, I want to update my personal information (email, PIN, or name) so that my account records stay current.
S8 (Validation): As a developer, I want the system to generate unique account numbers automatically to prevent duplicate account errors.
S9 (Error Handling): As a user, I want to receive clear error messages (e.g., "Insufficient Balance") so I understand why a transaction failed.
S10 (Delete Account): As a user, I want to permanently delete my account if I no longer need the service, ensuring my data is removed.
Sprint 1: Foundation & Core Security
Goal: Build the system skeleton, data storage, and secure access.
Capacity: 100 Hours ¦ Planned Load: 90 Hours ¦ Buffer: 10 Hours
Story ID | Story Name | Priority | Estimated Man-Hours | Status
S1 | Create Account (UI + Logic) | High | 30 | In Progress
S3 | PIN Authentication (Security) | High | 20 | To Do
S4 | Deposit | High | 20 | To Do
S5 | Withdraw Money (Logic + Balance Check) | High | 20 | To Do
S8 | Unique Account IDs (Validation) | High | 10 | To Do
TOTAL |  |  | 100 / 100 Hours
Sprint 2: Transactions & Account Management
Goal: Enable money movement and user profile control.
Capacity: 100 Hours ¦ Planned Load: 100 Hours ¦ Buffer: 0 Hours
Story ID | Story Name | Priority | Estimated Man-Hours | Status
S6 | View Account Details (Read Ops) | Low | 10 | Backlog
S9 | Error Msgs | Med | 10 | Backlog
S7 | Update Info (Edit Profile UI) | Med | 30 | Backlog
S10 | Delete Account (Cleanup Logic) | Low | 10 | Backlog
S2 | Data Persistence (JSON Setup) | High | 40 | Backlog
TOTAL |  |  | 100 / 100 Hours